## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2221-swen-261-04-07-team7
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a User I want to add a single product to the shopping cart so that I may proceed to purchase it. | Given I want a product when I add a product to the shopping cart then I expect the item to be added to the list in the shopping cart. | Pass | JLN 10/29
| Given I added a product to the shopping cart When I checkout and look at the price Then I expect the price to go up accordingly | Pass | JLN 10/29
As a User I want to remove items from my shopping cart so that I can longer purchase them. | Given I no longer want a product when remove the item from my shopping cart then I expect the item to no longer be in the shopping cart. | Pass | JLN 10/29
| Given An item has been removed from my shopping cart When I checkout and look at the price Then I expect the price to go down accordingly | Pass | JLN 10/29
As a User I want buy the products in my shopping cart so that I may receive them. | Given I want to receive the product when pay for the items in my shopping cart then I expect to receive the product at a later date. | Pass | JLN 10/29
As a buyer, I want to be able to view the products, so I can see which ones I want to purchase | Given a working backend when a user opens the shop then they should see a display of all the products | Pass | JLN 10/29
As a buyer, I want to be able to view a product's full details, so that I can better understand what the product is | Given working backend when a user clicks on a product then the entire product's details are displayed | Pass | JLN 10/29
| Given a valid product when a user opens the product's page then a button to add the item to the shopping cart will appear | Pass | JLN 10/29
As a user, I want to be able to search for a product, so I can view every single product with the name I provide. | Given a working backend when a buyer searches for an item then they should see a list of all items that match that item | Pass | JLN 10/29
| Given a displayed list of items when the buyer clicks on an item then it should display that item | Pass | JLN 10/29
As a user, I want to be able to set my own unique username, so that I have agency over the security of my account and access to it. | Given a valid UTF-8 string for a username when a user attempts to login with it then it retrieves their information and updates their shopping cart. | Pass | JLN 10/29
As a user, I want the website to keep track of what is in my cart, so that I don't have to put everything back in again when I log out. | Given user is having any activity when the user is logged in then store the entire account information in the server. | Pass | JLN 10/29
As a developer, I want to be able to send a REST request to add a specific product to a user's shopping cart, so that the user can manage their shopping cart. | Given a valid product and a valid user when send the request to add it to a user's shopping cart then it to be added to a user's shopping cart | Pass | JLN 10/29
As a developer, I want to be able to send a REST request to remove a specific product from a user's shopping cart, so that the user can manage their shopping cart. | Given a valid product and a valid user when send the request to remove it from a user's shopping cart then it to be removed from a user's shopping cart | Pass | JLN 10/29
As the administrator, I want to be able to remove products from the inventory, so that no users purchase a card I cannot send them. | Given admin submits a product object to be removed when the product exists then the product is removed and the inventory's UI is updated to reflect that | Pass | JLN 10/29
As the administrator, I would like to be able to add or remove products using a special administrator control panel, so that I dont have to navigate and search through the e-store to add or remove products. | Given the store is active when I remove a product using the administrator panel, that product will be removed immediately from the e-store. | Pass | JLN 10/29
| Given the store is active when I add a product using the administrator panel, that product will be added immediately from the e-store. | Pass | JLN 10/29
| Given the panel is intractable when I open the panel then I should see a list of all available products on the store. | Pass | JLN 10/29
| Given the store is active when I edit a product using the administrator panel, that product will be edited immediately from the e-store. | Pass | JLN 10/29
As the administrator, I would like to be able to click on and edit a specific product, so that I can change what is available on my site. | Given that the store is active, when I edit a product using the admin panel, that product will be automatically updated in the product database. | Pass | JLN 10/29
As the administrator, I want to be able to add new products to my inventory so that as I receive new cards my customers can become aware that I have it in stock. | Given admin submit a product object when there is no identical product exists in inventory then add submitted product to inventory and return code 200 (OK) | Pass | JLN 10/29
| Given admin submit a product object when identical product already exists in inventory then increment stock quantity of the product in the inventory and return code 200 (OK) | Pass | JLN 10/29
SPRINT 3 USER STORIES STARTS HERE
As a buyer, I should be able to purchase my card, so I can own my custom card | Given that I am on the shopping cart page, then I want to ber able to checkout all of my items. | Pass | JLN 11/8
| Given that I am on my custom card page, I want to be able to add the custom card to my shopping cart. | Pass | JLN 11/8
| Given that I am on the shopping cart page, then I want to be able to check out the item and have it removed from my shopping cart. | Pass | JLN 11/8
As a user or an owner, I should be able upload an image, so I can create a custom card | Given a valid .png or .jpeg when the user uploads it then the user's card should reflect the image they upload. | Pass | JLN 11/8
| Given a valid .png or .jpeg when the user saves the card then the user's card should be stored on the server until it is deleted | Pass | JLN 11/8
| If a buyer creates a card then it should only be visible for the buyer | Pass | JLN 11/8
| If an owner creates a card then it should be visible for all users | Pass | JLN 11/8
As a buyer or owner, I should be able to specify up to three move fields, so I can create a custom card with the moves I want on it | Given there are less than 3 moves on the card when a user submits a move then that move should be added to the card | Pass | JLN 11/8
| Given that I want to check out my card when I view the card, then I should see those moves updated on my card | Pass | JLN 11/8
As a buyer or owner, I should be able to specify the health of my card, so I can create a custom card | Given health has not been specified when a user submits a valid number then that number should be added as the card's health | Pass | JLN 11/8
| Given health has been specified when a user submits a valid number, then the older number should be replaced | Pass | JLN 11/8
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. | Pass | JLN 11/8
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. | Pass | JLN 11/8
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. | Pass | JLN 11/8
| Given that I am on the products page when there are products in the inventory then I see each product and short description. | Pass | JLN 11/8
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. | Pass | JLN 11/8
As a buyer or owner, I should be able specify a name for my card, so I can create a custom card | Given a valid name when a user supplies the name then their custom card should be updated to reflect that name | Pass | JLN 11/8
As a user I want to see how much my cart costs so I know how much I am spending | Given a shopping cart with >= 1 items in it when I navigate to the shopping cart then I expect to see the total price of the cart | Pass | JLN 11/8
As a user, I want to look at a nice clean user interface while I browse the website, so that I do not get lost, confused, turned around or angry. | Given I visit the website when I go to the home page then I expect to see accesible buttons and links, aswell as images, high contrast design. | Pass | JLN 11/8
| Given I visit the website when I go to the product page then I expect to see accesible buttons and links, aswell as images, high contrast design. | Pass | JLN 11/8
| Given I visit the website when I go to the login page then I expect to see accesible buttons and links, aswell as images, high contrast design. | Pass | JLN 11/8